## Shopenzer Testcases
|  |  |  | Date | 2022-11-16
|  |  |  | Team ID | PNT2022TMID17906
|  |  |  | Project Name | Project - Natural disaster Intensity Analyisis and Claasification
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
HomePage_TC_001 | UI | Home Page | Verify all the UI elements in Home page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Peratchi Srinitish
HomePage_TC_002 | Functional | Home Page | Verifiy the Data Entry page can be reachable. |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the Check Price button. | - | User should navigate to All upload Pages | Working as expected | Pass |  | N |  | Dhanush Sundareson
ImageUploadPage_TC_001 | UI | Image upload Page | Verify all the UI elements in Image upload page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3. Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Ponsurya
ImageUploadPage_TC_002 | Functional | Image upload Page | Verify user is able to upload images |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if all the mentioned type of images can be uploaded | jpg images | User should be able to upload all types of images in the page. | Working as expected | Pass |  | N |  | Vishnu Venkatraman
ImageUploadPage_TC_003 | Functional | Image upload Page | Verify proper classfication of the image is produced |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if all the mentioned type of images can be uploaded 6.Press the submit button | jpg images | User should be able to view the classfication produced by the model. | Working as expected | Pass |  | N |  | Arunpandian
VideoUploadPage_TC_001 | UI | Video upload Page | Verify all the UI elements in Image upload page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3. Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Ponsurya
VideoUploadPage_TC_002 | Functional | Video upload Page | Verify user is able to upload images |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if all the mentioned type of video files can be uploaded | mp4,wav,mvi files | User should be able to upload all types of video files in the page. | Working as expected | Pass |  | N |  | Peratchi Srinitish
VideoUploadPage_TC_003 | Functional | Video upload Page | Verify proper classfication of the image is produced |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if all the mentioned type of video files can be uploaded 6.Press the submit button | mp4,wav,mvi files | User should be able to view the classfication produced by the model. | Working as expected | Pass |  | N |  | Vishnu Venkat raman
LiveStreamPage_TC_001 | UI | Live stream Page | Verify all the UI elements in Image upload page rendered properly |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3. Verify all the UI elements displayed or not | - | All the UI elements rendered properly | Working as expected | Pass |  | N |  | Arunpandian
LiveStreamPage_TC_001 | Functional | Live stream Page | Verify user is able to live stream video |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if the user is able to live stream video | Live video through webcam | User should be able to live stream the video of the disaster | Working as expected | Pass |  | N |  | Dhanush Sundareson
LiveStreamPage_TC_001 | Functional | Live stream Page | Verify proper classfication of the image is produced |  | 1.Enter URL and click go 2.Verify all the UI elements displayed or not. 3.Press the submit button in the upload page. 4. Verify all the UI elements displayed or not 5. Verify if the user is able to live stream video 6.Press the submit button | Live video through webcam | User should be able to view the classfication produced by the model. | Working as expected | Pass |  | N |  | Vishnu Venkat raman

## Testscearnios
Test Scenarios
1 | Verify user is able to see home page?
2 | Verify user is able to navigate to data entry page?
3 | Verify user is able to see data entry page?
4 | Verify user is able to enter values in the fields?
5 | Verify user is able to navigate to output display page?
6 | Verify user is able to view the output display page?
7 | Veriify user is able to view the car resale value output in the output display page?